## Project
Project Schedule
| Project Name: | Chat Application Using WebSockets
| Project Start Date | 2022-02-01 | [5 empty] | Display Week | 1 |  | Week 6372 | [6 empty] | Week 6373 | [6 empty] | Week 6374 | [6 empty] | Week 6375 | [6 empty] | Week 6376 | [6 empty] | Week 6377 | [6 empty] | Week 6378 | [6 empty] | Week 6379
| Project Lead | Pradip Gohil | [8 empty] | 2022-01-31 | [6 empty] | 2022-02-07 | [6 empty] | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21
[11 empty] | 2022-01-31 | 2022-02-01 | 2022-02-02 | 2022-02-03 | 2022-02-04 | 2022-02-05 | 2022-02-06 | 2022-02-07 | 2022-02-08 | 2022-02-09 | 2022-02-10 | 2022-02-11 | 2022-02-12 | 2022-02-13 | 2022-02-14 | 2022-02-15 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-19 | 2022-02-20 | 2022-02-21 | 2022-02-22 | 2022-02-23 | 2022-02-24 | 2022-02-25 | 2022-02-26 | 2022-02-27 | 2022-02-28 | 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 0 | 0
WBS | TASK/Module | Name of the person | LEAD | PREDECESSOR | START | DEADLINE | END | DAYS | % DONE | WORK DAYS | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
1 | Overall Analysis
1.01 | Chat App Demo analysis | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-01 | 2022-02-02 | 2022-02-02 | 1 |  | 6 | bar: T to W
1.02 | Logic Behind The Application | Vishruti Agrawal/Hardik Rajput | Vishruti Agrawal |  | 2022-02-02 | 2022-02-03 | 2022-02-03 | 1 | bar: W to T
1.03 | Chat Application Overview | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-04 | 2022-02-05 | 2022-02-05 | 1 | bar: F to S
1.04 | Chat App theme settings | Vishruti Agrawal | Hardik Rajput |  | 2022-02-06 | 2022-02-07 | 2022-02-06 | 1 | bar: S to M
1.05 | Server Environment | Hardik Rajput | Hardik Rajput |  | 2022-02-06 | 2022-02-07 | 2022-02-07 | bar: S to M
1.06 | Frontend Overview & Analysis | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-06 | 2022-02-07 | 2022-02-08 | bar: S to M
1.07 | Backend Overview & Analysis | Hardik Rajput | Hardik Rajput |  | 2022-02-06 | 2022-02-07 | 2022-02-09
2 | Chat App Page Analysis
2.01 | Register New Users | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-07 | 2022-02-08 | 2022-02-08 | 1 |  | 8 | bar: M to T
2.02 | Verification if Already Registered | Vishruti Agrawal/Hardik Rajput | Vishruti Agrawal |  | 2022-02-08 | 2022-02-09 | 2022-02-09 | 1 | bar: T to W
2.03 | Redirect To Login Page | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-08 | 2022-02-09 | 2022-02-09 | bar: T to W
2.04 | Add links To Login page after registeration | Vishruti Agrawal/Hardik Rajput | Vishruti Agrawal |  | 2022-02-08 | 2022-02-09 | 2022-02-09 | 1 | bar: T to W
2.05 | Display User's Profile | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-11 | 2022-02-12 | 2022-02-12 | 1 | bar: F to S
2.06 | Analysis of User's Profile | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-12 | 2022-02-13 | 2022-02-13 | 1 | bar: S to S
2.07 | Create ChatRoom To Chat | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-13 | 2022-02-14 | 2022-02-14 | 1 | bar: S to M
2.08 | Add Options To Edit Profile | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-14 | 2022-02-15 | 2022-02-15 | 1 | bar: M to T
2.09 | Display User's Login Status in Database | Vishruti Agrawal | Hardik Rajput |  | 2022-02-15 | 2022-02-16 | 2022-02-16 | 1 | bar: T to W
3 | Working On Frontend | bar: W
3.01 | Analysis Of various frontend(CSS) frameworks | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-16 | 2022-02-16 | 2022-02-16 | 1 |  | 3 | bar: W
3.02 | Analysis of themes for card layout and navigation bar | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-16 | 2022-02-16 | 2022-02-16 | bar: W
3.03 | Analyze and Apply ChatRoom(Admin Panel) Theme | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-16 | 2022-02-16 | 2022-02-16
4 | Chat App Designing
4.01 | Create SignIn/SignUp Page | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-16 | 2022-02-16 | 2022-02-16 | 1 |  | 4 | bar: W
4.02 | CSS for ChatRoom Page | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-17 | 2022-02-17 | 2022-02-17 | bar: T
4.03 | CSS for Sliding Menu | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-18 | 2022-02-18 | 2022-02-18 | bar: F
4.04 | CSS for Profile Page | Vishruti Agrawal | Vishruti Agrawal |  | 2022-02-18 | 2022-02-18 | 2022-02-18 | bar: F
5 | Understanding Of Libraries | bar: S
5.01 | Php Management Tool - Composer(Software) | Vishruti Agrawal/Hardik Rajput | Hardik Rajput |  | 2022-02-19 | 2022-02-19 | 2022-02-19 | 1 | bar: S
5.02 | Download Ratchet Library For WebSockets | Vishruti Agrawal/Hardik Rajput | Hardik Rajput |  | 2022-02-19 | 2022-02-19 | 2022-02-19
6 | Management Of Database
6.01 | Manage user's details while registeration | Hardik Rajput | Hardik Rajput |  | 2022-02-19 | 2022-02-19 | 2022-02-19 | 1 |  | 1 | bar: S
6.02 | Manage User's details while editing profile | Hardik Rajput | Hardik Rajput |  | 2022-02-19 | 2022-02-19 | 2022-02-19 | bar: S
6.03 | Manage/Update User's Login Status while user logged in/out | Hardik Rajput | Hardik Rajput |  | 2022-02-19 | 2022-02-19 | 2022-02-19 | bar: S
7 | Understanding Of Web Sockets
7.01 | What is Socket Programmjng ? | Vishruti Agrawal/Hardik Rajput | Vishruti Agrawal/Hardik Rajput |  | 2022-02-21 | 2022-02-21 | 2022-02-21 | 1 |  | 2 | bar: M
7.02 | How To Implement Web Sockets On Localhost? | Vishruti Agrawal/Hardik Rajput | Vishruti Agrawal/Hardik Rajput |  | 2022-02-21 | 2022-02-21 | 2022-02-21 | bar: M
7.03 | Set Up Ports On localhost to run web sockets | Vishruti Agrawal/Hardik Rajput | Vishruti Agrawal/Hardik Rajput |  | 2022-02-22 | 2022-02-22 | 2022-02-22 | 1 | bar: T
7.04 | Install Ratchet Library | Vishruti Agrawal/Hardik Rajput | Vishruti Agrawal/Hardik Rajput |  | 2022-02-22 | 2022-02-22 | 2022-02-22 | bar: T
8 | Implement Chat
8.01 | Connection Of Websocket on Server(local) | Vishruti Agrawal/Hardik Rajput | Vishruti Agrawal/Hardik Rajput |  | 2022-02-23 | 2022-02-23 |  | 1 |  | 7 | bar: W
8.02 | Test connection over multiple Browsers | Vishruti Agrawal/Hardik Rajput | Vishruti Agrawal/Hardik Rajput |  | 2022-02-24 | 2022-02-24 |  | 1
8.03 | Connect Multiple Users & implement Chatting | Vishruti Agrawal/Hardik Rajput | Vishruti Agrawal/Hardik Rajput |  | 2022-02-26
8.04 | Load Chat of one to one Users & group chatting from database | Vishruti Agrawal/Hardik Rajput | Vishruti Agrawal/Hardik Rajput